## Slide 1
PROJECT MERIDIAN
Enterprise Data Platform Transformation
Executive Governance Review · Q1 2025
Programme Sponsor: Sarah Whitfield, Chief Data Officer
Delivery Partner: Apex Consulting
Client: NovaTech Solutions
Review Date: 24 January 2025
STRICTLY CONFIDENTIAL
NovaTech Solutions & Apex Consulting | © 2025 Apex Consulting

## Slide 2
EXECUTIVE SUMMARY · PROGRAMME HEALTH DASHBOARD
● OVERALL: AT RISK
62%
Programme Progress
vs 68% planned
£4.1M
Budget Utilised
of £7.2M total
14
Open Issues
3 critical
11 / 18
Milestones Achieved
this quarter
WORKSTREAM STATUS AT A GLANCE
Workstream | Lead | RAG | Progress | Key Concern
Data Ingestion & Pipelines | A. Thornton | ON TRACK | 78% | On schedule; UAT in Feb
Cloud Infrastructure (AWS) | D. Okafor | AT RISK | 55% | Env. provisioning delayed 2wks
Data Governance & Quality | P. Navarro | AT RISK | 48% | Policy sign-off pending
Analytics & Reporting | L. Yamamoto | ON TRACK | 71% | Phase 1 dashboards delivered
Security & Compliance | R. Mbeki | OFF TRACK | 32% | IAM framework gaps — critical
Change & Training | C. Harrington | AT RISK | 40% | Stakeholder engagement low
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 2

## Slide 3
PROGRAMME MILESTONES · Q4 2024 – Q3 2025
Kickoff
& Discovery
Oct '24
Infra
Blueprint
Nov '24
Data Model
Approval
Dec '24
Dev Sprint
Complete
Jan '25
UAT
Start
Feb '25
Security
Signoff
Mar '25
Go-Live
Phase 1
Jun '25
Completed
In Progress
Planned
KEY MILESTONE DETAIL
Milestone | Due Date | Owner | Status | Comment
Dev Sprint Complete (Phase 1 modules) | 31 Jan 2025 | A. Thornton | IN PROGRESS | 3 of 5 modules complete; 2 carry into Feb
Security & IAM Framework Sign-off | 28 Feb 2025 | R. Mbeki | OFF TRACK | IAM gaps identified; revised plan due 10 Feb
UAT Commencement — Analytics Platform | 14 Feb 2025 | L. Yamamoto | ON TRACK | Test scripts ready; business testers confirmed
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 3

## Slide 4
BUDGET & FINANCIAL TRACKING
£7.2M
Total Budget
Approved
£4.1M
Spent to Date
57% consumed
£7.6M
Forecast at Completion
+£0.4M variance
£0.38M
Contingency Remaining
of £0.6M available
SPEND BY WORKSTREAM (£'000)
Chart: 
| Data Pipelines | Cloud Infra | Data Governance | Analytics | Security | Change Mgmt
Budget | 1800 | 2100 | 900 | 1200 | 650 | 550
Actual / Forecast | 1420 | 1310 | 390 | 870 | 250 | 180
MONTHLY SPEND TREND vs PLAN (£'000)
Chart: 
| Oct | Nov | Dec | Jan | Feb | Mar
Planned Cumulative | 580 | 1250 | 2100 | 3050 | 4100 | 5200
Actual Cumulative | 460 | 1100 | 1890 | 2750 | 3600 | 4800
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 4

## Slide 5
RISK REGISTER · TOP PROGRAMME RISKS
2 Critical (5×5)
5 High (4+ score)
7 Medium
4 Low
ID | Risk Description | Category | Owner | Likelihood | Impact | Rating | Mitigation / Action
R01 | IAM framework gaps may block production deployment of secure data zones | Security | R. Mbeki | High (4) | Critical (5) | 20 | Remediation plan in review; interim controls in place; deadline 14 Feb
R02 | Key AWS environment provisioning slippage threatens Feb UAT window | Infrastructure | D. Okafor | High (4) | High (4) | 16 | Escalated to AWS account team; workaround environment commissioned
R03 | Data Governance policy sign-off delayed due to stakeholder availability | Governance | P. Navarro | Medium (3) | High (4) | 12 | Governance Committee slot booked 5 Feb; pre-read issued
R04 | Change fatigue: business engagement below target for training uptake | People | C. Harrington | Medium (3) | Medium (3) | 9 | Targeted engagement campaign; senior sponsor communications planned
R05 | Third-party data quality for legacy migration worse than estimated | Data | A. Thornton | Low (2) | High (4) | 8 | Automated profiling in place; cleansing sprint added to backlog
R06 | Programme resource attrition — 2 senior engineers at risk of leaving | Resourcing | Programme Mgr | Low (2) | High (4) | 8 | HR retention review initiated; knowledge transfer in progress
R07 | Regulatory change (DORA) may require rework to resilience architecture | Regulatory | R. Mbeki | Low (2) | Medium (3) | 6 | Monitoring DORA guidance; architecture review on standby
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 5

## Slide 6
ISSUES LOG · OPEN ISSUES REQUIRING ATTENTION
14 Total Open
3 Critical
5 High
9 Resolved this month
ID | Issue Description | Workstream | Raised By | Priority | Due Date | Resolution / Action
I01 | Production-grade encryption keys not yet provisioned for data-at-rest in S3 zones | Security | R. Mbeki | Critical | 10 Feb 25 | AWS KMS setup in progress; security team review 7 Feb
I02 | Legacy ETL jobs failing intermittently due to schema mismatch in source system | Data Pipelines | A. Thornton | Critical | 31 Jan 25 | Hotfix deployed; permanent fix targeted EOW
I03 | Business sign-off on data dictionary blocked pending Legal review of PII classifications | Governance | P. Navarro | Critical | 14 Feb 25 | Legal review scheduled 6 Feb; owner escalating
I04 | Test environment refresh SLA breached — 48hr delay to UAT readiness | Cloud Infra | D. Okafor | High | 7 Feb 25 | Infrastructure automation script being corrected
I05 | Power BI licensing shortfall — 15 analyst seats not yet provisioned | Analytics | L. Yamamoto | High | 14 Feb 25 | Procurement request raised; approval pending CFO sign-off
I06 | Training content for Data Stewards not reviewed by SMEs — 2wk overdue | Change & Training | C. Harrington | High | 28 Jan 25 | SME review session booked 30 Jan; content frozen after
I07 | API rate limiting on source system causing pipeline throughput degradation | Data Pipelines | A. Thornton | High | 14 Feb 25 | Throttling config under review with vendor
I08 | DPIA not yet initiated for new customer analytics module | Governance | P. Navarro | Medium | 28 Feb 25 | DPO engaged; DPIA workshop scheduled 12 Feb
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 6

## Slide 7
DECISIONS REQUIRED FROM EXECUTIVE SPONSORS
D01
Approve Revised Security Remediation Timeline
Owner: CDO / CISO · Decision needed by: 31 Jan 2025
The IAM framework gaps (Risk R01) require an additional 3-week remediation sprint. This pushes the Security Sign-off milestone from 28 Feb to 21 Mar 2025.
Option A: Approve revised timeline — accept 3-week delay to overall programme (recommended)
Option B: Maintain Feb deadline — accept elevated risk with interim compensating controls
D02
Authorise Additional Budget — AWS Infrastructure Overrun
Owner: CFO / Programme Board · Decision needed by: 7 Feb 2025
Cloud infrastructure costs are tracking £400K above original estimate due to higher-than-anticipated data egress charges and additional compute needed for backfill runs.
Option A: Release £400K from programme contingency (contingency balance: £380K — shortfall of £20K)
Option B: Approve supplementary budget of £420K via Change Control process (recommended)
D03
Confirm Go-Live Approach: Big Bang vs Phased Rollout
Owner: CDO / CTO · Decision needed by: 14 Feb 2025
Original plan assumes a single go-live in June 2025. Given current delays, the team proposes a phased approach — Analytics in June, Data Platform in Aug — reducing deployment risk.
Option A: Proceed with phased rollout (Jun + Aug) — lower risk, business continuity maintained (recommended)
Option B: Maintain big-bang June go-live — higher risk but avoids dual running of legacy and new platforms
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 7

## Slide 8
NEXT STEPS · KEY ACTIONS FOR FEBRUARY 2025
# | Action | Owner | Due | Priority
1 | Finalise and present IAM remediation plan to Security Review Board | R. Mbeki | 7 Feb | Critical
2 | Raise Change Control for additional AWS infrastructure budget (£420K) | Programme Mgr | 7 Feb | Critical
3 | Convene Governance Committee to sign off Data Policy v2.0 | P. Navarro | 5 Feb | Critical
4 | Fix legacy ETL schema mismatch — deploy permanent patch to production | A. Thornton | 31 Jan | High
5 | Submit Power BI licence procurement request for CFO approval | L. Yamamoto | 3 Feb | High
6 | Complete SME review and freeze Change & Training content | C. Harrington | 30 Jan | High
7 | Provision corrected test environment refresh automation script | D. Okafor | 7 Feb | High
8 | Initiate DPIA workshop with DPO for new analytics module | P. Navarro | 12 Feb | Medium
9 | Confirm executive decision on Go-Live approach (D03) | CDO / CTO | 14 Feb | Medium
10 | Deliver monthly programme status report to Steering Committee | Programme Mgr | 28 Feb | Standard
📅 Next Executive Governance Review: 28 February 2025 · 09:00–10:30 · Boardroom 4B / Virtual
NovaTech Solutions & Apex Consulting · Strictly Confidential · Q1 2025 · Slide 8